## Sheet1
EPIC | SEPTEMBER |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DECEMBER
| WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14 | WEEK 15
Documentation
Conceptual Specification | bar: SEPTEMBER WEEK 2 to OCTOBER WEEK 5
Technical Specification | bar: SEPTEMBER WEEK 3 to OCTOBER WEEK 7
Client Prototype Implementation | bar: OCTOBER WEEK 8 to DECEMBER WEEK 15
Server Prototype Implementation | bar: NOVEMBER WEEK 11 to DECEMBER WEEK 15
Dependency Graph Visualization Prototype | bar: DECEMBER WEEK 13 to DECEMBER WEEK 15
Dependency Graph Visualization Alpha Demo | bar: DECEMBER WEEK 15